# 04 · Execute & Collaborate

Audience: team leads, team members, PMs · Time: 30 minutes Prerequisite: modules 01 & 03 · Screens: Execute group + Strategy & Knowledge

## Learning objectives

Run the daily delivery loop: boards, own tasks, timesheets, the Work Inbox and

Focus Planner — plus the collaboration surfaces (docs, boards, proofing,

feedback) that keep knowledge in the platform.

## 1. Boards (#/boards)

Kanban execution of the plan:

Columns mirror task status (To Do → In Progress → In Review → Done).

Drag a card between columns — status updates flow to EVM, health and

dashboards instantly.

Cards show owner, project, priority and due date; overdue cards are marked.

Filter by project, owner or swimlane (assignee/team).

The same board engine powers Agile Delivery (`#/agile`) with sprints for teams that prefer sprint cadence over continuous flow.

## 2. Resources (#/resources)

Capacity management for the PMO:

Each resource has a capacity (h/week) and current allocation from task

assignments.

The view highlights over-allocations (>100% load) — the same hot spots

surface on the Executive dashboard.

Use Planning Lab → Resource leveling for prescriptions on how to rebalance

without breaking the critical path.

## 3. Timesheets (#/timesheets) — the fuel line

Timesheets convert effort into cost and earned value. Every downstream number

(actual cost, CPI, budget burn, freshness) depends on them.

As a team member:

Open Timesheets — the week grid shows your assigned tasks.

Enter hours per day; add a note where useful.

Submit for approval. Your entry locks to edits until returned.

As an approver (PM/PMO):

Open the approvals queue — submissions by person and project.

Check hours against plan; approve or return with comment.

Approved hours immediately:

post actual cost (Financials),

update earned value (EVM),

refresh data-freshness scores (Integrity),

fire TIMESHEET_APPROVED automations (e.g. notify finance).

Training message to repeat: **no timesheets = the platform goes blind.** Freshness rails turn "timesheet hygiene" into a visible, scored KPI.

## 4. Work Inbox (#/inbox)

The personal action list — the default home for delivery roles:

Everything awaiting you: task assignments, approvals, review requests,

gate decisions, mentions.

Work top-down; each item deep-links to its record.

Empty inbox = nothing pending on you today.

## 5. Focus Planner (#/planner)

A personal time-blocking view over your tasks and meetings:

See your week, drag tasks into focus blocks.

Balances planned effort against capacity so you over-commit consciously.

Pairs with Timesheets: plan the week on Monday, log it on Friday.

## 6. Field Operations (#/field)

For site/field teams: capture progress, observations and photos against tasks

from the field; updates attach to the project record and feed health.

## 7. Strategy & Knowledge

| Screen | Use it for |
| --- | --- |
| Docs & Knowledge (#/docs) | Policies, SOPs, lessons learned — versioned, searchable from ⌘K |
| Message Boards (#/boards-hub) | Topic discussions per project/program (async status, decisions) |
| Proofing & Approvals (#/proofing) | Review deliverables with markup; approve/reject with an audit trail |
| Feedback & Roadmap (#/feedback) | Collect ideas, triage into the product/project roadmap |

All four are permission-gated and searchable — the point is *tribal knowledge

becomes institutional knowledge*.

## 8. Notifications (#/notifications)

Everything the platform pushed at you — mentions, approvals, alert breaches,

gate requests. Each notification deep-links to its record; the bell icon shows

the unread count.

## 9. Exercise (15 min) — a day in the life of a team member

Log in as liam@pmct.io (Technical Lead). Your home is the Work Inbox.

Open your assigned tasks; move one on the board to In Progress.

Open Timesheets — log 6h today on your task; submit.

Log in as pm.sarah@pmct.io → approve Liam's timesheet.

Back as Liam: check the Integrity screen (#/integrity) — did the freshness

score for your project improve? (Approvals are the #1 freshness driver.)

Post a status update on the project's Message Board; ⌘K to find it again.

Discussion: you just fed cost, EVM, health, freshness and reporting with

three clicks. What happens to the executive dashboard tonight?

## 10. Key takeaways

Boards and inbox = the daily loop; timesheets = the trust layer beneath every

financial and EVM figure.

Approvals cascade: timesheet → cost → EVM → alerts → automations → dashboards.

Keep knowledge in Docs/Boards/Proofing so ⌘K finds it, not your inbox.