# 05 · Control Performance

Audience: PMs, finance controllers, PMO · Time: 45 minutes Prerequisite: modules 01 & 03 · Screens: Control group

## Learning objectives

Operate the control loop: budgets and actuals in Financials, performance

measurement in EVM, exposure in RAID, governed change in Change Control, and

decision gates in Stage Gates & Governance — with Data Integrity as the trust

check.

## 1. Financials (#/financials)

The cost truth of the portfolio:

Baseline budget (approved) vs current budget (post-change) vs

actual cost (posted actuals) vs forecast/EAC.

Actuals arrive from approved timesheets and direct-cost entries — they are

never typed onto the dashboard.

Budget utilisation % and variance are shown per project and rolled up.

Finance roles (FINANCE) manage budgets; everyone else views.

## 2. Clients & Billing (#/clients)

Commercial layer: client accounts, contracts, billing schedules and invoices

linked to projects; ties revenue to delivery.

## 3. Investment & Business Case (#/investment)

Pre-approval stage: business case, NPV/IRR-style justification, funding rounds

and benefits tracking — connecting "why we started" to "what we achieved".

## 4. EVM (#/evm) — the instrument panel

Earned Value Management per project and in portfolio aggregate:

| Metric | Meaning | Healthy |
| --- | --- | --- |
| PV planned value | Budgeted cost of work scheduled | — |
| EV earned value | Budgeted cost of work performed | — |
| AC actual cost | Cost of work performed | — |
| CPI = EV/AC | Cost efficiency | ≥ 0.95 |
| SPI = EV/PV | Schedule efficiency | ≥ 0.95 |

Period close: EVM is computed per period (status date) — the latest close

feeds the Executive gauges.

Per-project view: CPI/SPI columns, trend lines, variance explanations.

Breach rules: when indices cross thresholds, an EVM_BREACH alert is

raised and automations fire (e.g. notify the sponsor).

Variances are measured against the baseline (module 03) — no baseline,

no honest variance.

## 5. Health (#/health)

Project health is a computed score (0–100) blending schedule, cost, RAID and

milestone signals into RAG:

Health changes are captured historically — the dashboard shows recent

movements (e.g. Amber → Red).

HEALTH_CHANGED is an automation trigger: a project going red can

automatically summon the PMO.

## 6. RAID (#/raid) — Risks, Assumptions, Issues, Dependencies

Log the item with type, severity, owner, score (probability × impact),

mitigation and status.

Top-scored risks flow to the Executive dashboard automatically.

RAID_CREATED triggers automations (e.g. alert the program board for CRITICAL

items).

Close items with resolution notes — the register stays audit-clean.

## 7. Change Control (#/changes)

The governed route to change scope/schedule/cost:

Raise a Change Request — description, reason, impacted scope.

The platform attaches impact analysis (schedule/cost deltas vs baseline).

Workflow: Submitted → Assessed → Approved / Rejected — every transition is

audited.

Approved CRs update the current budget and justify a new baseline.

CHANGE_REQUESTED triggers notifications to the approver chain.

## 8. Stage Gates (#/gates)

Phase checkpoints (Initiate → Plan → Execute → Close):

Each gate has criteria and evidence attached to a project phase.

Approvers (gate.decide permission — executives, PMO) Pass / Hold / Fail

with comments; the decision is audited.

Pending gates appear on the Executive dashboard governance queue and on the

Leadership bundle.

## 9. Governance (#/governance)

The single queue where governance work happens: pending gates, change requests

in flight, open alerts and their states — the "governance section" of every

steering meeting runs off this screen.

## 10. Data Integrity (#/integrity) — trust, scored

Every project gets a freshness score (0–100) from the recency of its

feeds: timesheets, actuals, health captures, EVM periods. The **worst feed

dominates** — one stale feed drags the score down and names itself.

Levels: GREEN healthy → WARN → DEGRADE → CRITICAL (score < 40).

The rule taught to every user: below 40, do not decide — chase the feed.

AI-assisted remediation actions can be drafted here for human review.

## 11. Prioritization (#/prioritization)

Score and rank projects/programs (value, risk, strategic fit) to guide

funding decisions — feeding the Investment screen.

## 12. Exercise (20 min) — the control loop

Log in as pm.sarah@pmct.io; open EVM — find your project's CPI/SPI.

Are you delivering under budget? Ahead of schedule?

Open RAID; log a CRITICAL risk ("vendor insolvency"); add mitigation.

Open the Executive dashboard (or ask the facilitator) — is the risk in Top

Risks yet?

Open Changes; raise a CR to extend the schedule by two weeks. Note the

impact analysis.

As facilitator (PMO): approve the CR in Governance; verify the audit

trail (Administration → Audit Trail).

Check Data Integrity — which project needs timesheets chased?

Discussion: which of these steps would have been email + spreadsheet in a

traditional PMO? What did the audit trail capture for free?

## 13. Key takeaways

Financials ↔ EVM ↔ Health form the measurement triangle; baselines make it

honest; timesheets make it true.

RAID, Changes and Gates are the three governance muscles — all audited.

Integrity scores convert "data hygiene" into a managed KPI with a stop rule.