# 08 · Hands-On Workshop

Audience: mixed groups (exec / PM / team) · Time: 90 minutes Prerequisite: modules 01–04 attended · Format: three parallel stations, rotate every 25 minutes, debrief together.

## Setup (facilitator, before the session)

Platform running; each participant has a laptop and login (see module 01).

Verify the reference project PRJ-CZR-FLOW is intact: 364 tasks, 44

critical, finish 2028-04-01, FLW-001 float 521. It is the "healthy plan"

the stations compare against.

Optional reset: npm run db:seed:node restores pristine demo data.

## Station A — The Executive's Eye (25 min)

Persona: COO / sponsor. Login: ceo@pmct.io.

Open the Executive Control Tower. From the telemetry strip alone, write

the three issues you would raise in a steering meeting.

Use the EVM dials: are CPI/SPI healthy? Which side (cost/schedule) needs

attention?

Drill: Forecast tile → EVM control → identify the worst project → return →

click its cluster in Earned Value by Project.

Project Health Matrix: click the Red (or Amber) slice — how many

projects sit there?

Integrity Core: find the project with the lowest freshness score. Would

you decide on its numbers today?

Finish in Leadership Control Tower: which single section would you take

into a board pack?

Deliverable: a 3-bullet verbal briefing — situation, risk, decision needed.

## Station B — The PM's Workbench (25 min)

Persona: project manager. Login: pm.sarah@pmct.io.

Create project PRJ-WORKSHOP (start next Monday, 3-week duration).

WBS: phases Initiate → Design → Build → Handover; 2 tasks each with

owners (use the seeded team) and effort.

Schedule: link phases finish-to-start; open the Network view —

identify the critical path and its total float.

Run the Plan doctor; fix all findings (orphans, unassigned effort);

re-run until clean.

Baseline the plan ("Workshop baseline v1").

RAID: log one CRITICAL risk with mitigation; Changes: raise one CR

(extend build by 1 week) and note the impact analysis.

EVM: explain to your neighbour why this new project shows no indices

yet — and what event will create them.

Deliverable: a baseline-backed plan with a clean doctor score and two

governance records.

## Station C — The Team Member's Day (25 min)

Persona: technical lead. Login: liam@pmct.io.

Work Inbox: work through pending items — what is oldest?

Boards: move one assigned task to In Progress; open a second task and

double-click its due date to edit inline.

Timesheets: log 6h Monday–Wednesday on your tasks; add one note;

submit.

As approver (facilitator logs in as pm.sarah@pmct.io): approve Liam's

timesheet — watch for the cascade (cost → EVM → freshness).

Focus Planner: block two hours tomorrow for your hardest task.

Docs & Knowledge: find the project SOP; Message Boards: post a short

status update; ⌘K to verify both are findable.

Deliverable: a submitted-and-approved timesheet plus an updated board.

## Group debrief (15 min) — connect the stations

Ask, in this order:

Station C approved hours → where did the money appear? (Financials.)

Where did the performance appear? (EVM.) Where did trust improve?

(Integrity freshness.)

Station B's CR → whose queue does it land in? *(Governance — visible on

the Executive dashboard.)*

Station A's red project → which station's inputs would fix its freshness

score? (Station C's timesheets.)

What would this cost a traditional PMO in emails, spreadsheets and slide

decks — and what just happened in 75 minutes with three people?

## Scoring (optional, competitive)

| Checkpoint | Points |
| --- | --- |
| Station A: correct 3-bullet briefing | 10 |
| Station B: doctor score 100 + baseline created | 15 |
| Station B: CR raised with impact analysis | 5 |
| Station C: timesheet approved by approver | 10 |
| Station C: board + inbox cleared | 5 |
| Any station: freshness score improved on Integrity | 5 |

## Facilitator notes

The demo DB is small (one active portfolio) — that is deliberate: participants

see the whole system, not a forest of rows.

If a station finishes early: have Station A explore Reporting Center

subscriptions; Station B model a "what-if" in the Planning Lab; Station C ask

the AI Assistant a question about their own tasks.

Watch the clock at rotations — the debrief is where the mental model locks in.